# Project Planning Management

## Project Proposal

- Project Name : Global Happiness Analysis: Economic, Health, and Social Factors

- Problem Statement : This project analyzes differences in happiness levels across countries from 2015 to 2023 and explores their relationships with economic, health, and social factors.

- Project Objectives :

- Compare happiness scores across countries and years.
- Identify countries with the highest and lowest happiness scores.
- Analyze trends and changes in happiness levels over time.
- Explore relationships between happiness, GDP per capita, healthy life expectancy, and social support.
- Present key findings through interactive dashboards.

- Dataset Description : The project uses the World Happiness Dataset 2015–2023, containing 1,367 records, 171 distinct countries, and 11 geographical regions. The dataset includes happiness scores and economic, health, and social indicators

- Data source : Kaggle

- Tools : Excal || Power Query || Power pi

## Project Plan & Gant

| Project Phase | Duration | Start Date | End Date |
| --- | --- | --- | --- |
| Data Understanding | 5 | 21/10 | 25/10 |
| Cleaning Data | 5 | 26/10 | 30/10 |
| Data Analysis | 6 | 31/10 | 5/11 |
| Dashboard (Excel) | 10 | 6/11 | 15/11 |
| Dashboard (Power Pi) | 10 | 6/11 | 15/11 |
| Results Review & Testing | 5 | 16/11 | 20/11 |
| Documentation & Final Presentation | 5 | 21/11 | 25/11 |

## Task Assignment & Roles

| Name | Role |
| --- | --- |
| Abdallah khaled Fathalla | Project Documentation & Final Presentation |
| Youssef Mohamed Nabil Algazzar | Dashboard Testing, KPI Validation, Comparison & Business Questions Validation |
| Ahmed Mohammed Roshdy fahim | Excel Data Cleaning & Preparation |
| Lotfy Abdulhamed Ahmed ElBadawy | Power BI Data Cleaning, Data Modeling & DAX Measures |
| Malak Osama Mohamed Afifi | Power BI Dashboard Development & Design |
| Eman Ghoneim Zakaria Elghandour | Excel Dashboard Development |

## Risk Assessment & Mitigation plan

| Risk | Mitigation Plan |
| --- | --- |
| 1. Missing or Inconsistent Data | Inspect the dataset, identify missing values, and standardize data formats before analysis. |
| 2. Differences in Economic and Social Indicators | Verify the definitions and measurement scales of indicators such as GDP, income, social support, and political satisfaction to ensure accurate comparisons. |
| 3. Misinterpreting the Relationship Between Happiness and Its Influencing Factors | Use appropriate visualizations and statistical analysis to identify relationships while avoiding unsupported conclusions about cause and effect. |
| 4. Inaccurate Calculations or Data Analysis | Validate calculations and KPIs using Excel and Power BI, and cross-check results against the original dataset |
| 5. Incomplete or Misleading Dashboard Visualizations | Design clear and appropriate charts, test filters and interactions, and ensure that the dashboard accurately represents the relationships between happiness and its economic, social, and political indicators |

## KPLs

1-Global Average Happiness Score
2-Top Region by Happiness
3-Highest Recorded Happiness Score
4-Lowest Recorded Happiness Score
5-Global Happiness Growth Trend (2015 vs 2023)
6-Avg Social Support Contribution
7-Avg GDP per Capita Contribution
8-Avg Healthy Life Expectancy Contribution
9-Avg Freedom to Make Life Choices
10-Avg Perceptions of Corruption Impact